## Project Details
Project name | Cloud risk and compliance(ISO 27001+SOC2+NIST)
Scenario | A company is migrating HRMS and customer data to AWS cloud. The objective is to identify risks and implement controls aligned with ISO 27001,SOC2 and NIST

## Dashboard
INTEGRATED CLOUD RISK AND COMPLIANCE(ISO 27001+SOC2+NIST) DASHBOARD
KPI Metrics
Metric | Value
Total risks | 20
High risks | 8
Medium risks | 7
Low risks | 5
Top High Risks Table
|  | Risk Level | Count
|  | High | 8
|  | Medium | 7
|  | Low | 5

## Risk Register
ID | Asset | Threat | Vulnerability | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk(H/L/M) | Control | ISO Control | SOC 2 | NIST
1 | Customer database | Data breach | weak passowrd pplicy | 5 | 5 | 25 | High | MFA implementation | A.9 | CC6 | PR.AC
2 | AWS S3 Bucket | Data exposure | Public access enabled | 5 | 5 | 25 | High | Restrict public access | A.9 | CC6 | PR.AC
3 | Admin Accounts | Unauthorized access | No MFA | 4 | 5 | 20 | High | Enforce MFA | A.9 | CC6 | PR.AC
4 | Cloud infrastructure | Misconfiguration | No configyration monitoring | 5 | 4 | 20 | High | Enable AWS configuration | A.12 | CC7 | DE. CM
5 | HRMS Data | Insider threat | Excessive access rights | 4 | 5 | 20 | High | RBAC | A.9 | CC6 | PR.AC
6 | API Gateway | API Abuse | no rate limiting | 4 | 4 | 16 | High | API throttling | A.13 | CC7 | PR. PT
7 | Backup data | data loss | no backup testing | 4 | 5 | 20 | High | backup validation | A.12 | CC7 | CP
8 | Cloud logs | log tampering | no log protection | 4 | 4 | 16 | High | enable log integrity | A.12 | CC7 | AU
9 | Employee accounts | phishing | lack of awareness | 4 | 3 | 12 | Medium | security training | A.7 | CC2 | AT
10 | Cloud database | SQL Injection | No input validation | 3 | 4 | 12 | Medium | input validation | A.14 | CC7 | SI
11 | Web application | XSS Attack | poor coding practices | 3 | 4 | 12 | Medium | secure coding | A.14 | CC7 | SI
12 | Network | DDoS attack | no protection | 3 | 4 | 12 | Medium | AWS Shield | A.13 | CC7 | SC
13 | IAM Roles | Privilege escalation | misconfigured roles | 3 | 4 | 12 | Medium | least privilege | A.9 | CC6 | PR.AC
14 | Data transfers | data interception | no encryption | 3 | 4 | 12 | Medium | TLS encryption | A.10 | CC6 | SC
15 | Vendor systems | Third party breach | no vendor assessment | 3 | 4 | 12 | Medium | vendor audit | A.15 | CC3 | SR
16 | Endpoints | malware | outdated antivirus | 2 | 3 | 6 | Low | endpoint protection | A.12 | CC7 | SI
17 | Workstations | Unauthorized access | no auto-lock | 2 | 3 | 6 | Low | auto screen lock | A.11 | CC6 | PE
18 | Email system | spam | weak filters | 2 | 3 | 6 | Low | email filtering | A.13 | CC7 | SI
19 | Logs | log loss | no retention policy | 2 | 3 | 6 | Low | log retention | A.12 | CC7 | AU
20 | Backup storage | unauthorized access | weak access control | 2 | 3 | 6 | Low | access restriction | A.9 | CC6 | PR.AC

## Control mapping
Risk ID | Risk | ISO 27001 Control | SOC2 Control | NIST Control | Control Description
1 | Data Breach | A.9 Access control | CC6 Logical access | PR.AC | Restrict access using authentication controls
2 | S3 Data exposure | A.9 Access control | CC6 Logical access | PR.AC | restrict public access to storage
3 | Unauthorised admin access | A.9 Access control | CC6 Logical access | PR.AC | enforce MFA
4 | Cloud misconfiguration | A.12 Operations security | CC7 Monitoring | DE. CM | Continuous configuration monitoring
5 | Insider threat | A.9 Access control | CC6 Logical access | PR.AC | Role-based access control
6 | Abuse | A.13 Network security | CC7 Monitoring | PR. PT | Implement API Throttling
7 | Data loss | A.12 Operations security | CC7 Monitoring | CP | Backup and recovery testing
8 | Log tampering | A.12 Operations security | CC7 Monitoring | AU | enable log integrity controls
9 | phishing | A.7 Awareness | CC2 | AT | Security awareness traiing
10 | SQL Injection | A.14 Secure development | CC7 Monitoring | SI | input validation
11 | DDoS Attack | A.13 Network security | CC7 Monitoring | SC | Network protection controls
12 | Third party risk | A.15 Supplier securty | CC3 | SR | vendor risk assessment

## System of Applicabilty(SoA)
1 | Scope | This Statement of Applicability applies to cloud-hosted HRMS and customer data systems deployed on AWS.
2 | Control Selection Criteria | Controls are selected based on risk assessment results and aligned with ISO 27001, SOC2, and NIST frameworks.
3 | Included Controls | Example:
A.9 Access Control → Included
Reason: To prevent unauthorized access to sensitive data
A.12 Operations Security → Included
Reason: To ensure secure system operations
A.13 Network Security → Included
Reason: To protect network infrastructure
A.7 Human Resource Security → Included
Reason: To reduce human-related risks
4 | Excluded Controls | A.11 Physical Security → Excluded
Reason: Managed by AWS cloud provider
A.8 Asset Management (partial) → Excluded
Reason: Cloud assets managed by provider
5 | Control status | Control | status
|  | A.9 | Implemented
|  | A.12 | In progress
|  | A.13 | Planned

## Risk treatment plan
Risk ID | RIsk | treatment | owner | timeline | Status
1 | Data breach | Implement MFA | Security team | 30 days | Planned
2 | S3 Bucket data exposure | disable pulic access and enable bucket policies with least privelege | Cloud/devops team | 15 days | In progress
3 | Cloud misconfiguration | enable configuration monitoring tools and periodic audits | cloud security teams | 20 days | Planned
4 | Data loss | Implement the automated backups and conduct regular backup restoration testing | IT Operations team | 25 days | Planned
5 | Phishing attacks | Conduct employee security awareness training and phishing simulations | HR+Security team | 45 days | Planned